{"text_format":"3","workbook":"xlsx","n_sheets":2,"sheets":["周工作情况总结","项目明细表"],"read":"whole","date_system":"1900"}

{"sheet":"周工作情况总结","index":0,"n_rows":113,"n_cols":7,"rows_kept":113,"merged":[[2,2,10,2],[3,1,5,1],[3,3,5,3],[3,4,5,4],[6,1,7,1],[6,3,7,3],[6,4,7,4],[8,1,10,1],[8,3,10,3],[8,4,10,4],[11,2,14,2],[15,2,21,2],[22,2,29,2],[24,3,25,3],[30,2,37,2],[33,3,34,3],[33,4,34,4],[33,5,34,5],[33,6,34,6],[38,2,42,2],[43,2,48,2],[49,2,52,2],[53,2,63,2],[59,3,60,3],[61,3,63,3],[64,2,72,2],[66,3,68,3],[69,3,71,3],[73,2,78,2],[76,3,78,3],[76,6,78,6],[79,2,85,2],[82,3,84,3],[86,2,92,2],[90,3,92,3],[93,2,98,2],[96,3,98,3],[99,2,105,2],[103,3,105,3],[106,2,112,2],[110,3,112,3]]}
[]
[null,"序号","时间","工作内容","内容说明","完成情况","备注"]
[null,"1","3月第一周","华智定制开发项目梳理","人员调整后，重点项目、重点局点做到专项专人。","除前端工程等新入职人员外，其它项目均有专人一、一对接。"]
[null,"2",null,"云桌面产品培训","由西安研发中心的主线产品测试经理做了完整的产品部署、配置培训。","+ 在公司搭建了WorkSpace和LearningSapce，所有参加培训的人员均完成培训后测试。"]
[{"$nulls":5},"+ 对vGPU、网关等高级配置有了实战演练。"]
[{"$nulls":5},"+ 西安研发的对外支持首选让我们对接，他们做技术支持。"]
[null,"5",null,"公司内IT平台规划","新光线平台、ECM平台、文档库、四算系统、代码库。","建立使用规范，统一各IT平台的支撑人员。"]
[{"$nulls":5},"拟新增项目商机管理系统（支持云桌面项目）"]
[null,"7",null,"云屏V1.2版","增加语音设置日程、语义识别、用户意图识别等AI能力、新增课程表视图。","此版本发版后占缓新功能规划。修改当前平台的bug，系统调优，优化交互逻辑。"]
[{"$nulls":5},"硬件增加麦克风"]
[{"$nulls":5},"测试自己的STT服务（现在为腾讯STT）"]
[null,"8","3月第二周","软件开发事业部全体月度会议","全体月度会议，宣布新的内部小组调整，工作管理规范，开发工作规范等。"]
[null,"9",null,"协助华智IT尽快上线VDI下单的IT系统","配合华智IT，实现PMS下单到OA审核流程的IT上线。"]
[null,"10",null,"上线云桌面LLM+RAG","私域部署LLM+RAG，实现对华三云桌面文档库的全面解析，支持云桌面售前、服务人员使用","已在ima中验证可行性和输出质量。"]
[null,"11",null,"软件开发事业部人员调整到位","云南两人员、前端高级开发工程师、云数外包人员","云南项目和人员工时纳入新光线。","与华三云桌面产线研发的协作与边界"]
[null,"12","3月第三周","西安开发组人员落实","和朱岳落实西安的人员人），重庆相应调整","暂停"]
[null,"13",null,"细化上周大会后，研发部月度会议贡献奖的评价细致"]
[null,"14",null,"内部IT系统的论坛启用+LLM智能问答系统","先期应用于开发部和VDI部","已上线（Dify+ DeepSeek API）"]
[null,"15",null,"SpaceOS+NingOS的部署验证","和西安测试已经商量好了终端借货，可以由我们自己烧录操作系统","已确认，sapceOS在虚拟机和本地的瘦终端上都安装"]
[null,"17",null,"内部IT系统统一用户认证改造","将当前各IT系统的用户、密码体系整合。","暂缓"]
[null,"19",null,"湖南VDI项目实施支持","和熊白杨沟通了全程支持该项目的前端部署、实施。","代理商"]
[null,"20",null,"几个定制项目的落实","AIOPS、商客包50万、西安高新",null,"咸阳高新华智已计收"]
[null,"21","3月第四周","Answer系统上线，本周技术交流会","29篇帖子，本周主题MCP","完成"]
[null,"22",null,"PMS系统上线","PMS数据和OA打通",null,"已完成"]
[null,"23",null,"SIP系统确定","研究现有SIP系统代码","订单手动录入？"]
[null,"24",null,null,"打通订单、发货信息和License","License打通还是录入？","导入"]
[null,"25",null,"云桌面AI助手","仅供内部和可控用户使用。","提供了三个工具（喜报、技术文章和配置单，配置单还需要优化）","已完成"]
[null,"26",null,"在公司内部搭建Citrix和Vmware环境","确定onStor之外的分布式系统可行性。","Vmware的超融合搭建","协调硬件"]
[null,"28",null,"环业项目","给了第一版项目方案",null,"等用户反馈"]
[null,"27",null,"和西安的开发协同","按照华三的安全管理，前期的远端开发终端全被收回。","需要和H3C把云桌面相关的开发重新确定一下边界、方式等。"]
[null,"28","4月第一周","基于医疗垂直行业的AI应用","32B本地模型+RAG+智能硬件","方案ppt+终端可演示\n和客户、市场进行交流"]
[null,"29",null,"测试工作","海光+终端","海光4号服务器+新合作伙伴的终端","海光服务器已完成测试"]
[null,"30",null,"基于华智定开今年的产品讨论会","包括云南组，确定从华智拿过来的代码层以及包装的产品","确定了产品后进行第二轮人员调整","周二，已完成。"]
[null,"31",null,"SIP系统确定","1、项目信息管理\n2、项目产品清单\n3、发货管理\n4、发货明细\n5、对外售后查询","4月2周第一版","表结构、无原型，AI为主生成代码。采购golang+vue3"]
[null,"32"]
[null,"34",null,"人员招聘","公司内IT开发人员","包括IT系统开发、运维、和华智、华三数据的对接"]
[null,"35",null,"环业项目、AIOPS项目",null,"1. 第二轮沟通\n2. 原型设计完成","环页项目给出初步报价"]
[null,"35",null,"光线工作日志平台新功能上线","1、项目需求管理\n2、新的工作日志填写模块",null,"已上线"]
[null,"35","4月第二周","新硬件测试","海光CPU+英伟达显卡（T4）","已配合西安完成用例、压力测试","完成"]
[null,"35",null,"华智PMS+OA审批上线","华智PMS已基本完成，拟增加（项目总结页签）联动激活OA审批流程","本周和华智IT联调完成上线","完成"]
[null,"35",null,"云桌面SIP系统第一版","1、项目信息管理\n2、项目产品清单\n3、发货管理\n4、发货明细\n5、对外售后查询\"","支持多用户、权限分配。本周交付第一版","完成"]
[null,"35",null,"汇智AI研发赋能交流会","1、介绍Trae+LLM完成一个数据库系统的培训。\n2、IMA使用","周一下午"]
[null,"36",null,"AIOPS电力开发模块","原型已确认，下开发工作单。",null,"进行"]
[null,"37","4月第三周","SIP系统培训+上线","给VDI销售管理人员打开相关模块功能","周三","和俊杰、晟罡重新讨论了方案。"]
[{"$nulls":3},"云玑安装和测试","初步的判断","安装盘很小（不带虚拟化）\n文档比H3C差\nsocket5代理很小的安装包","安装已完成"]
[null,"38",null,"给华三400开放两个接口API",null,null,"未完成"]
[null,"39",null,"云玑平台的进一步测试和对比报告","同配置可开虚拟机数量"]
[null,"40",null,"研发部，结构调整","行业/安平合并。重点项目小组管理，其它项目统一管理。进一步精简人员、提高人效。"]
[null,"41",null,"人员变动后的重点交接工作",null,"18号完成"]
[null,"43","4月第四周","PMS+OMS+SIP","正在要求华智开放PMS的第三方访问。"]
[null,"44",null,"南岸政府智能应用展","已提供宣传材料","配合刘畅提供材料和演示场景"]
[null,"45",null,"行业开发项目","1、杭州工厂项目\n2、中国天辰"]
[null,"46",null,"定开部门新架构和考核方案","本周完成方案过会，并向部门全体宣贯。"]
[null,"47","5月第三周","企业双软认证","已提交企业双软认证材料"]
[null,"48",null,"CMMI3认证","和机构开了前期准备会，准备前期材料。",null,"暂停"]
[null,"48",null,"马上消费调研反馈","和云桌面研发共同对客户的6大问题进行了回复。"]
[null,"49",null,"AIOPS电力巡检功能","完成功能开发，和业务口同步功能设计"]
[null,"50",null,"华三400SIP","和华三数据中台完成两个接口的数据开发工作，6月12号后不再提供手动数据表"]
[null,"51",null,"公司OMS系统","完成原型设计，在功能上保证和当前的SIP能平滑升级。","数据结构保持一致，功能能复用"]
[null,"52",null,"云桌面相关","oVirt平台验证","oVirt系统是一套包含服务器虚拟化、分布式存储、桌面虚拟化，传输协议以及客户端的完整开源方案"]
[{"$nulls":4},"三方硬件移植"]
[null,"53",null,"重点项目","和云南团队验证便携式智能视频分析仪","海光3号+国产GPU","去年出货17台，今年有15台的项目空间。"]
[null,"54",null,null,"高新公安模型功能演示","安平业务交接"]
[null,"55",null,null,"数图一体化收款"]
[null,"56","5月第四周","oVirt测试完毕","服务器虚拟化到虚拟机池化","云桌面管理账号和协议账号需自己做","Spark协议优化，测试openstack"]
[null,"57",null,"OMS的一阶段功能上线","合同明细+发货+基础数据","二阶段的功能规划","下一阶段首先做项目商机（是否要和四算系统对接）"]
[null,"58",null,"重要项目","高新公安模型","云南参与"]
[{"$nulls":4},"乐山公安","四川的定开资金使用"]
[null,"59",null,null,"广州荔湾"]
[null,"60",null,"人员管理","安平人员调整"]
[null,"61",null,null,"本周5月绩效考核","研发人员绩效方案"]
[null,"62",null,null,"新岗位人员招聘"]
[null,"63",null,"中移物联","专项的200万使用","60+60+80，正在配合招标前文件。"]
[null,"64","6月第一周","IT人员到岗和服务器搬迁","1701配电房","需工程部配合"]
[null,"65",null,"OMS系统第二阶段开发工作","SIP部分已经上线，本周完成项目商机填报","可以提供相关的报表"]
[null,"66",null,"联系拜访信创桥","做一次线上交流"]
[null,"67",null,"重点项目","录像快取设备项目内部立项",null,"2季度定开计收"]
[null,"68",null,null,"高新公安模型","配合业主提交文档，本周找业主落实最后4个模型"]
[null,"69",null,null,"大庆公安项目"]
[null,"70","6月第二周","OA/四算系统调整","流程及流程节点调整"]
[null,"71",null,"OMS上线两新模块","项目商机和项目订单模块上线","商机/订单/合同/发货"]
[null,"72",null,"信创桥/RemoteAPP技术交流","win10pro下多线程运行应用的技术方案","本周到公司做技术交流","是否公司内部立项"]
[null,"73",null,"重点项目","录像快取设备项目内部立项","快取软件/硬盘直读"]
[null,"74",null,null,"高新公安模型","业主交流，剩余4个模型已开始编码"]
[null,"75",null,null,"科目一使用云桌面","文件十五五完成全国3000点的无盘站改造","海成科技"]
[null,"76",null,"人员调整","测试人员调至VDI事业部","已和晟罡沟通"]
[null,"77","6月第三周","OMS系统","统计模块，电子合同模块","商机模块已全面培训/启用"]
[null,"78",null,"信创桥","网络版平台已部署，和对方技术进行了一天的技术交流。","关键技术、存在的问题、市场反馈、竞争对手情况等。"]
[null,"79",null,"开发规划","信创桥的网络版","http://showdoc.unissense.tech/web/#/655974214/274925445","我们从底层操作系统定制开始做"]
[null,"80",null,"中移物联","徐栋梁内部汇报完成。招标前准备","是集中招还是分包招"]
[null,"81",null,"重点项目","高新公安模型","6月30日完成交付的10个模型开发工作"]
[null,"82",null,null,"四川办的催款问题","四川办的欠的人天数量比较大，并且不断再交付新工作量。"]
[null,"83",null,null,"其它交付项目","北京公交总队、内蒙省厅升级、中国政法大学、陕西柠条塔升级"]
[null,"85","6月第四周","人员调整","已减少前端一人（王九云），拟招一名C++/QT开发人员，熟悉linux操作系统开发","该人员可作为信创桥客户端开发和SpaceOS开发用"]
[null,"86",null,"UNISSENSE.TECH | UNISSENSE.TOP | UNISSPACE.COM","三个域名的备案和工信部的合规接入","已完成"]
[null,"87",null,"华三400对接","已上线","后续解决一些特殊情况"]
[null,"90",null,"重点项目","高新公安模型","一阶段10个模型已上线，约在本周去和客户做交流展示。"]
[null,"91",null,null,"四川办结算","1264人天，徐凯协助和四川办开专项会议。"]
[null,"92",null,null,"录像快取设备项目","解决与华智同类产品的冲突问题，拿到EC201上当前部署的系统代码。钟文俊在边缘设备上部署新增功能。"]
[null,"93","7月第二周","云桌面预研","使用Gemini pro将信创桥的后台进行完整解读，数据库结构、虚拟机服务、配置管理、策略管理等。"]
[null,"93",null,"开箱即用平台","功能定义和核心功能验证。"]
[null,"94",null,"OMS系统","订单审批、代理商二维码查询、产品二维码查询"]
[null,"95",null,"人员调整","本周安平减少后端一名、行业减少前端一名","软件开发部人数调整到23人，空出人员窗口补充C++开发人员"]
[null,"96",null,"定开项目","新增6个项目，1个项目完成验收"]
[null,"97",null,null,"录像快取产品已和华智边缘产品负责人进行了沟通。采用C++定制（内存限制），和徐凯安排和王总（公安1所、3所定制项目）做了业务交流，探讨产品市场。","和公司当前的开发技术栈不符，项目停止"]
[null,"98",null,null,"华能集团基于云桌面账户体系的集中门户","约客户确定集成项目的具体情况。"]
[null,"93","7月第三周","云桌面预研","服务端/终端开发正常推进，人员需求确定。","终端引导windows、信创启动成功。"]
[null,"93",null,"开箱即用平台","北京东方亿盟，集智产品部署及分析","交流材料V2.0版"]
[null,"94",null,"OMS系统","加入流程引擎，实现订单审批，制造商管理（硬件包装盒二维码）、出入库管理"]
[null,"95",null,"人员调整","2人调入、优化1人、1人转VDI"]
[null,"96",null,"定开项目","新增6个项目，2个项目完成验收","四川沙湾项目计收"]
[null,"97",null,null,"云南孟定清水河智慧口岸AR项目发起验收","80万左右计收"]
[null,"98",null,null,"华能集团基于云桌面账户体系的集中门户","约客户确定集成项目的具体情况。"]

{"sheet":"项目明细表","index":1,"n_rows":24,"n_cols":7,"rows_kept":24,"merged":[[2,1,8,1],[9,1,16,1],[17,1,23,1]]}
[]
[]
[null,"7月第二周","中车安网二期项目","山东",{"v":470000,"d":"470,000.00"},"新增项目","项目已报单，待启动开发"]
[null,null,"抚远市检查站巡检","黑龙江",{"v":32000,"d":"32,000.00"},"新增项目","项目已报单，待启动开发"]
[null,null,"南通通州湾师范区雪亮工程二期工程扩容项目","江苏",{"v":32000,"d":"32,000.00"},"新增项目","提前交付协议，预计Q3下单核销"]
[null,null,"万通华智安消一体化","吉林",{"v":5910,"d":"5,910.00"},"验收项目","已提供验收报告"]
[null,null,"重庆高新三期","重庆",{"v":1000000,"d":"1,000,000.00"},"重点项目","合同已签订，开发交付阶段"]
[null,null,"乐山沙湾视觉计算项目","四川",{"v":210000,"d":"210,000.00"},"重点项目","提前交付协议，重点关注办事处核销时间"]
[null,null,"德阳市公安局","四川",{"v":138000,"d":"138,000.00"},"重点项目","提前交付协议，重点关注办事处核销时间"]
[null,"7月第二周","重庆市公安局江北区分局所需视频监控智能化建设项目--软件下单","重庆",{"v":29550,"d":"29,550.00"},"新增项目","项目已下单，待启动开发"]
[null,null,"立讯精密-锦溪园区AI算力扩容&安防设备采购项目","广东",{"v":27580,"d":"27,580.00"},"新增项目","项目已下单，核销提前交付协议，待提供验收报告"]
[null,null,"西部矿业智慧视觉建设项目","青海",{"v":19700,"d":"19,700.00"},"新增项目","项目已下单，待启动开发"]
[null,null,"娄底移动项目定制开发","湖南",{"v":1970,"d":"1,970.00"},"验收项目","已提供验收报告"]
[null,null,"疫情防控系统开发及相关服务采购项目-华智","内蒙古",{"v":181799.96,"d":"181,799.96"},"验收项目","已提供验收报告"]
[null,null,"重庆高新三期","重庆",{"v":1000000,"d":"1,000,000.00"},"重点项目","合同已签订，开发交付阶段"]
[null,null,"乐山沙湾视觉计算项目","四川",{"v":210000,"d":"210,000.00"},"四川","提前交付协议，重点关注办事处核销时间"]
[null,null,"内蒙GA厅平台升级","内蒙古","-","内蒙古","平台升级，工作量分析评估中"]
[null,"7月第三周","重庆烟草工业黔江烟厂易地技改项目-第四批定制增补","重庆",{"v":50000,"d":"50,000.00"},"新增项目","项目已报单，待启动开发"]
[null,null,"重庆师范大学极云二期","重庆",{"v":16000,"d":"16,000.00"},"新增项目","项目已报单，待启动开发"]
[null,null,"南京江宁教育联网","江苏",{"v":40000,"d":"40,000.00"},"新增项目","项目已报单，待启动开发"]
[null,null,"北京公交总队视频智能化项目","北京",{"v":28000,"d":"28,000.00"},"提前交付","协议签订，启动开发"]
[null,null,"北京市局视综二期项目","北京",{"v":8000,"d":"8,000.00"},"提前交付","协议签订，启动开发"]
[null,null,"乐山沙湾视觉计算项目/德阳市公安局","四川",{"v":250000,"d":"250,000.00"},"重点项目","提前交付协议，本周新增需求25人天，关注核销时间"]
[null,null,"内蒙GA厅平台升级","内蒙古",{"v":60000,"d":"60,000.00"},"重点项目","定制适配，保证升级"]